## Cover
TIDEWELL COFFEE CO.
Tidewell App 2.0
Project budget: plan, actuals and forecast
Status at | End of September 2026
Model checks | All 14 checks pass
Scenario | Current forecast
Version | 1.4, 12 October 2026
Owner | Project controls, Digital
What this workbook is for
The budget for Tidewell App 2.0, the coffee chain's new app for ordering ahead, paying at the counter and collecting rewards. It holds the plan the steering committee approved in March 2026, what has been spent since, and a forecast for the rest, so you can see where the project will land, why, and what the next decision costs.
Every month
1 Paste the month's export from the finance system at the bottom of the table on Actuals.
2 On Inputs, set Actuals through to that month.
3 Update the current plan where something changed: schedule, staffing, rates, purchases, change requests, progress.
4 Open Checks: every line should say OK. Then write the commentary on Report.
5 Share the Dashboard and the Report.
Sheets
Dashboard | Status, the key numbers and three charts for the steering committee | Output
Report | Budget, actual, forecast and variance for each cost line; contingency; earned value | Output
Monthly | Plan and actual + forecast per month, by group | Output
Inputs | Settings, what-if levers, schedule, cost lines, rates, staffing, platform costs, progress | Input
Purchases | One-off purchases and change requests | Input
Actuals | The finance system's export: one row per booking | Input
Calc | Every calculation, month by month | Calculation
Checks | Tests the model runs on itself | Check
Colour key
1250 | An assumption: type here. Inputs are the only unlocked cells.
1250 | Typed-in records: the actuals, the cost lines, the commentary.
1250 | Formula. Don't type over it: the sheet is protected so you can't by accident.
1250 | Formula that brings a number from another sheet (on Calc and Checks).
1250 | Current plan differs from the baseline (on Inputs and Purchases).
OK | Check passes. FAIL in red when it doesn't.
Sep-26 | A month with actuals. White months are forecast.
Conventions
• Amounts in US dollars, without sales tax. Costs are positive.
• Over (under): forecast minus budget. Positive means over budget, shown red; negative means under, shown green.
• Every timeline has the same 15 months, April 2026 to June 2027, in the same columns (F to T).
• Baseline: the plan approved on 12 March 2026. It doesn't change; changes go into the current plan.
• Forecast: actuals for the closed months, the current plan for the months after.
• No macros, no hidden sheets, no links to other files. Calculation and output sheets are protected without a password (Review > Unprotect Sheet).
Version history
1.0 12 Mar 2026 | Baseline approved by the steering committee
1.1 9 Jul 2026 | April to June actuals
1.2 11 Aug 2026 | July actuals; Android contractor added
1.3 10 Sep 2026 | August actuals; CR-01 wallet payments approved
1.4 12 Oct 2026 | September actuals; CR-02 approved; new test day rate; penetration test quote
Tidewell Coffee Co., its people and its suppliers are made up. This workbook is an example from goodaiguide.com/possible/the-budget, built by Claude Code.

## Dashboard
Tidewell App 2.0: budget status
End of September 2026 · Tidewell Coffee Co. · USD
● Amber: inside the approved budget, with less than 50% of the contingency left
Checks: All 14 checks pass · Scenario: Current forecast
Approved budget | Spent to date | Forecast at completion | Contingency left | Launch | Work per dollar
1925000 | 826535 | 1870855 | 54145 | 2027-01-01 | 0.85806
incl. $178k contingency | 43% of the budget · plan: $810k | +$124k against the base budget | 30% of the $178k reserve | On the approved date | $0.86 of planned work for each $1 spent
Cumulative spend |  |  | What moves the forecast
Approved plan against actual to date plus forecast. The shaded months are forecast. |  |  | Forecast minus budget per cost line, largest first
Contingency |  |  | Decisions this month
What has used the $178k reserve so far |  |  | Numbers to have ready for the steering committee
|  |  | One more month of build would cost |  | 187245
|  |  | The contingency left pays for |  | 0.28917
|  |  | Pending change requests, not yet decided |  | 46000
|  |  | Contingency left if they are approved |  | 8145
|  |  | Forecast at today's work per dollar |  | 2095763.9887
|  |  | … against the approved budget |  | 170763.9887
Work per dollar: the cost performance index on Report.
A month of build: the current plan's build team and platform for one month.
Data behind the charts
Formulas only. The charts and the colours above read these cells.
Status | Amber | Amber: inside the approved budget, with less than 50% of the contingency left
Checks failing | 0 | Scenario | Current forecast | Months late | 0
Over (under) budget by cost line |  |  | Largest first |  | Over | Under | Room
Product management | 0 | 5.1e-08 | Approved changes | 59500 | 59500 | 0 | -45675
Product design | -21875 | 21875 | Android development | 41040 | 41040 | 0
iOS development | -780 | 780 | Product design | -21875 | 0 | -21875
Android development | 41040 | 41040 | Quality assurance | 21660 | 21660 | 0
Backend & integrations | 0 | 5.5e-08 | Cloud hosting | 12800 | 12800 | 0
Quality assurance | 21660 | 21660 | Test devices | 5040 | 5040 | 0
Cloud & DevOps | 3625 | 3625 | All other lines | 5445 | 5445 | 0
Engineering lead | 0 | 5.8e-08
User research & testing | 0 | 5.9e-08
Security & accessibility | 2500 | 2500
Payment certification | 1700 | 1700
Test devices | 5040 | 5040
Launch content | 0 | 6.3e-08
Cloud hosting | 12800 | 12800
Software & tools | -1830 | 1830
Third-party services | 230 | 230
Approved changes | 59500 | 59500
Contingency reserve
Approved changes | 59500
Overruns | 64110
Left | 54145
Reserve | 177755

## Report
Budget report
Budget, actuals and forecast by cost line, at the end of September 2026. USD.
|  | To date |  |  | At completion |  |  |  | Commentary
Cost line | Budget | Plan | Actual | Over (under) | Still to spend | Forecast | Over (under) | % | What changed
Team
Product management | 159500 | 87000 | 87000 | 0 | 72500 | 159500 | 0 | 0%
Product design | 143750 | 100000 | 84375 | -15625 | 37500 | 121875 | -21875 | -15.22% | Second designer started mid-May; one designer at 75% on another project since July
iOS development | 224640 | 98280 | 97500 | -780 | 126360 | 223860 | -780 | -0.3472%
Android development | 218880 | 95760 | 109440 | 13680 | 150480 | 259920 | 41040 | 18.75% | Extra contractor since August to recover the Android delay, kept until launch
Backend & integrations | 329000 | 161000 | 161000 | 0 | 168000 | 329000 | 0 | 0%
Quality assurance | 126000 | 45360 | 52080 | 6720 | 95580 | 147660 | 21660 | 17.19% | Second tester since September; TestHarbor's new day rate from October
Cloud & DevOps | 90625 | 32625 | 36250 | 3625 | 58000 | 94250 | 3625 | 4% | Extra DevOps time for the September load tests
Engineering lead | 173250 | 90750 | 90750 | 0 | 82500 | 173250 | 0 | 0%
Team, total | 1465645 | 710775 | 718395 | 7620 | 790920 | 1509315 | 43670 | 2.98%
Purchases
User research & testing | 42000 | 24000 | 24000 | 0 | 18000 | 42000 | 0 | 0%
Security & accessibility | 46000 | 0 | 0 | 0 | 48500 | 48500 | 2500 | 5.435% | Penetration test quote came in higher than the estimate
Payment certification | 9500 | 9500 | 11200 | 1700 | 0 | 11200 | 1700 | 17.89% | Wallet payments (CR-01) widened the compliance review
Test devices | 16000 | 16000 | 17240 | 1240 | 3800 | 21040 | 5040 | 31.5% | Two extra older Android phones; older and foldable phones added after the first beta
Launch content | 22000 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0%
Purchases, total | 135500 | 49500 | 52440 | 2940 | 92300 | 144740 | 9240 | 6.819%
Platform
Cloud hosting | 70300 | 19300 | 25700 | 6400 | 57400 | 83100 | 12800 | 18.21% | Larger test environment and load tests during the build
Software & tools | 54000 | 24400 | 23770 | -630 | 28400 | 52170 | -1830 | -3.389% | Two unused design seats cancelled
Third-party services | 21800 | 6000 | 6230 | 230 | 15800 | 22030 | 230 | 1.055%
Platform, total | 146100 | 49700 | 55700 | 6000 | 101600 | 157300 | 11200 | 7.666%
Changes
Approved changes | 0 | 0 | 0 | 0 | 59500 | 59500 | 59500 |  | CR-01 wallet payments and CR-02 allergen info, funded from the contingency
Changes, total | 0 | 0 | 0 | 0 | 59500 | 59500 | 59500
Total project cost | 1747245 | 809975 | 826535 | 16560 | 1044320 | 1870855 | 123610 | 7.075%
Contingency
The reserve on top of the base budget, and what has used it.
| Amount | Of the reserve
Approved budget | 1925000
Base budget (without contingency) | 1747245
Contingency reserve | 177755 | 100%
Used by approved changes | 59500 | 33.47%
Used by overruns on the plan | 64110 | 36.07%
Contingency left | 54145 | 30.46%
Pending changes, not in the forecast | 46000
Contingency left if they're approved | 8145
Earned value: a second opinion
Compares the work done with the money spent. If the rest of the project performs like the months so far, where does it land?
Phase | Budget | Work done | Earned value | Plan to date
Discovery | 48075 | 100% | 48075 | 48075
Design | 208370 | 100% | 208370 | 208370
Build | 905550 | 50% | 452775 | 553530
Launch prep | 428700 | 0% | 0 | 0
Hypercare | 156550 | 0% | 0 | 0
Whole project | 1747245 | 40.59% | 709220 | 809975
Cost performance index (CPI) | 0.85806 |  | Planned work delivered per dollar spent. Below 1.00: the work costs more than planned.
Schedule performance index (SPI) | 0.87561 |  | Planned work delivered per dollar of plan to date. Below 1.00: behind schedule.
Forecast at today's cost performance | 2036263.9887 |  | Actuals so far, plus the remaining planned work at today's cost per unit of work. Excludes changes.
With approved changes, over (under) budget | 170763.9887 |  | The same, with the approved changes added, against the approved budget.

## Monthly
Monthly view
Plan and actual + forecast per month, by group. USD.
Month | Total | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01
|  | Actual | Actual | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
Baseline plan
Team | 1465645 | 45875 | 87485 | 87485 | 163310 | 163310 | 163310 | 163310 | 163310 | 155350 | 155350 | 58775 | 58775 | 0 | 0 | 0
Purchases | 135500 | 0 | 24000 | 0 | 16000 | 0 | 9500 | 0 | 0 | 50000 | 36000 | 0 | 0 | 0 | 0 | 0
Platform | 146100 | 2200 | 4700 | 4700 | 12700 | 12700 | 12700 | 12700 | 12700 | 16000 | 16000 | 19500 | 19500 | 0 | 0 | 0
Changes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 1747245 | 48075 | 116185 | 92185 | 192010 | 176010 | 185510 | 176010 | 176010 | 221350 | 207350 | 78275 | 78275 | 0 | 0 | 0
Actual + forecast
Team | 1509315 | 45875 | 80455 | 87485 | 159405 | 168705 | 176470 | 173145 | 173145 | 163270 | 163270 | 59045 | 59045 | 0 | 0 | 0
Purchases | 144740 | 0 | 24000 | 0 | 17240 | 0 | 11200 | 0 | 0 | 56300 | 36000 | 0 | 0 | 0 | 0 | 0
Platform | 157300 | 2180 | 4700 | 4800 | 12970 | 13780 | 17270 | 14100 | 14100 | 16700 | 16700 | 20000 | 20000 | 0 | 0 | 0
Changes | 59500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 | 21500 | 0 | 0 | 0 | 0 | 0 | 0
Total | 1870855 | 48055 | 109155 | 92285 | 189615 | 182485 | 204940 | 187245 | 225245 | 257770 | 215970 | 79045 | 79045 | 0 | 0 | 0
Difference
Actual + forecast minus plan | 123610 | -20 | -7030 | 100 | -2395 | 6475 | 19430 | 11235 | 49235 | 36420 | 8620 | 770 | 770 | 0 | 0 | 0
Cumulative (the dashboard chart)
Baseline plan |  | 48075 | 164260 | 256445 | 448455 | 624465 | 809975 | 985985 | 1161995 | 1383345 | 1590695 | 1668970 | 1747245 | 1747245 | 1747245 | 1747245
Actual + forecast |  | 48055 | 157210 | 249495 | 439110 | 621595 | 826535 | 1013780 | 1239025 | 1496795 | 1712765 | 1791810 | 1870855 | 1870855 | 1870855 | 1870855
Approved budget |  | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000
Forecast months (chart shading) |  | 0 | 0 | 0 | 0 | 0 | 0 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000 | 1925000

## Inputs
Inputs
Every assumption the model uses. Change a blue cell and every sheet updates. Baseline columns hold the plan approved on 12 March 2026: leave them, and put changes in the current columns.
1 Project
Setting | Value | Unit
Company | Tidewell Coffee Co. |  |  | Shown in titles
Project | Tidewell App 2.0 |  |  | Shown in titles
Currency | USD |  |  | Shown in titles; amounts are not converted
First month of the project | 2026-04-01 |  |  | Every timeline starts here
Actuals through | 2026-09-01 |  |  | The last month finance has closed. Up to here: actuals. After it: forecast.
Contractor billable days per month | 18 | days |  | Days a day-rate contractor bills in an average month
Approved budget, including contingency | 1925000 | USD |  | Business case approved by the steering committee, 12 March 2026
Base budget at approval | 1747245 | USD |  | The phased plan as approved. Checks uses it to spot edits to the baseline.
Status turns amber below | 50% | of contingency left |  | Green above, amber below, red when the forecast exceeds the approved budget
2 What-if
Try a different future without touching the forecast. Set everything back to 0 / No for the official forecast.
Lever | Value | Unit
Include pending change requests | No |  |  | Yes adds the change requests still waiting for a decision (Purchases sheet) to the forecast
Contractor rate change | 0% |  |  | Applied to every contractor day rate in the forecast months, e.g. 5% for a rate rise
Extra months per phase | 0 | months |  | Set in the What-if column of the schedule below, per phase
Scenario shown | Current forecast
3 Schedule
Five phases back to back, in whole months. Baseline: the plan approved in March. Current: the engineering lead's plan at the status date.
| Months |  |  |  | Starts in month |  | Dates
Phase | Baseline | Current | What-if | Forecast | Baseline | Forecast | Baseline start | Baseline end | Forecast start | Forecast end
Discovery | 1 | 1 | 0 | 1 | 1 | 1 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 |  | Interviews, journeys, scope
Design | 2 | 2 | 0 | 2 | 2 | 2 | 2026-05-01 | 2026-06-01 | 2026-05-01 | 2026-06-01 |  | Flows, prototype, design system
Build | 5 | 5 | 0 | 5 | 4 | 4 | 2026-07-01 | 2026-11-01 | 2026-07-01 | 2026-11-01 |  | iOS, Android, backend and integrations
Launch prep | 2 | 2 | 0 | 2 | 9 | 9 | 2026-12-01 | 2027-01-01 | 2026-12-01 | 2027-01-01 |  | Beta, security and accessibility, store release
Hypercare | 2 | 2 | 0 | 2 | 11 | 11 | 2027-02-01 | 2027-03-01 | 2027-02-01 | 2027-03-01 |  | Fixes and tuning after launch
Whole project | 12 | 12 | 0 | 12 |  |  | 2026-04-01 | 2027-03-01 | 2026-04-01 | 2027-03-01
Launch: the end of Launch prep | [7 empty] | 2027-01-01 |  | 2027-01-01
Launch moves by | 0 | months
4 Cost lines
The project's chart of accounts. Actuals, plan and forecast all use these names.
Cost line | Group |  | What it covers
Product management | Team |  | Product manager (internal)
Product design | Team |  | UX and UI designers (internal)
iOS development | Team |  | iOS engineers from Brightlane Studio
Android development | Team |  | Android engineers from Parallel Apps
Backend & integrations | Team |  | Ordering, payments, rewards and POS integration (internal)
Quality assurance | Team |  | Test engineers from TestHarbor
Cloud & DevOps | Team |  | Infrastructure, releases and security engineering (internal)
Engineering lead | Team |  | Technical lead for the whole build (internal)
User research & testing | Purchases |  | Interviews and usability tests
Security & accessibility | Purchases |  | Penetration test and accessibility audit
Payment certification | Purchases |  | Card-payment compliance review
Test devices | Purchases |  | Phones and tablets for the test lab
Launch content | Purchases |  | App store screenshots, preview video, launch film
Cloud hosting | Platform |  | Development, test and production environments
Software & tools | Platform |  | Design, code, testing and monitoring tools
Third-party services | Platform |  | Maps, push notifications, text messages
Approved changes | Changes |  | Change requests the steering committee approved
5 Team rates
Internal staff at loaded monthly cost (salary, benefits, overhead). Contractors at a day rate.
Role (cost line) | Sourcing | Baseline rate | Current rate | Per | Baseline per FTE month | Forecast per FTE month
Product management | Internal | 14500 | 14500 | month | 14500 | 14500 |  | Loaded monthly cost from HR
Product design | Internal | 12500 | 12500 | month | 12500 | 12500 |  | Loaded monthly cost from HR
iOS development | Contractor | 780 | 780 | day | 14040 | 14040 |  | Brightlane Studio day rate, fixed until project end
Android development | Contractor | 760 | 760 | day | 13680 | 13680 |  | Parallel Apps day rate
Backend & integrations | Internal | 14000 | 14000 | month | 14000 | 14000 |  | Loaded monthly cost from HR
Quality assurance | Contractor | 560 | 590 | day | 10080 | 10620 |  | TestHarbor's new rate from October
Cloud & DevOps | Internal | 14500 | 14500 | month | 14500 | 14500 |  | Loaded monthly cost from HR
Engineering lead | Internal | 16500 | 16500 | month | 16500 | 16500 |  | Loaded monthly cost from HR
6 Staffing
Full-time equivalents (FTE) per month in each phase; 0.5 = half of one person's time. Baseline: the approved plan. Current: the engineering lead's staffing plan.
| Baseline | [5 empty] | Current
Role | Discovery | Design | Build | Launch prep | Hypercare |  | Discovery | Design | Build | Launch prep | Hypercare
Product management | 1 | 1 | 1 | 1 | 0.5 |  | 1 | 1 | 1 | 1 | 0.5
Product design | 1 | 2 | 1 | 0.5 | 0.25 |  | 1 | 2 | 0.75 | 0.5 | 0.25
iOS development | 0 | 0.5 | 2 | 2 | 0.5 |  | 0 | 0.5 | 2 | 2 | 0.5
Android development | 0 | 0.5 | 2 | 2 | 0.5 |  | 0 | 0.5 | 2.5 | 2.5 | 0.5
Backend & integrations | 0.5 | 1 | 3 | 2 | 1 |  | 0.5 | 1 | 3 | 2 | 1
Quality assurance | 0 | 0 | 1.5 | 2 | 0.5 |  | 0 | 0 | 2 | 2 | 0.5
Cloud & DevOps | 0.25 | 0.25 | 0.5 | 1 | 0.5 |  | 0.25 | 0.25 | 0.5 | 1 | 0.5
Engineering lead | 0.5 | 1 | 1 | 1 | 0.5 |  | 0.5 | 1 | 1 | 1 | 0.5
Team size | 3.25 | 6.25 | 12 | 11.5 | 4.25 |  | 3.25 | 6.25 | 12.75 | 12 | 4.25
7 Platform & tools
Monthly cost in each phase, from the providers' price lists and current invoices. Production hosting grows after launch.
| Baseline | [5 empty] | Current
Cost line (per month) | Discovery | Design | Build | Launch prep | Hypercare |  | Discovery | Design | Build | Launch prep | Hypercare
Cloud hosting | 400 | 1200 | 5500 | 8000 | 12000 |  | 400 | 1200 | 7200 | 9000 | 12500
Software & tools | 1800 | 3200 | 5400 | 5400 | 4000 |  | 1800 | 3200 | 5100 | 5100 | 4000
Third-party services | 0 | 300 | 1800 | 2600 | 3500 |  | 0 | 300 | 1800 | 2600 | 3500
Per month | 2200 | 4700 | 12700 | 16000 | 19500 |  | 2200 | 4700 | 14100 | 16700 | 20000
8 Progress
How much of each phase's work is done at the status date: the engineering lead's estimate. Feeds the earned-value check on Report.
Phase | Work done
Discovery | 100% |  | Done
Design | 100% |  | Done
Build | 50% |  | Ordering and rewards done, payments and POS integration under way
Launch prep | 0% |  | Not started
Hypercare | 0% |  | Not started
Formulas:
Dates = EDATE(StartMonth,[Starts in month]-1)
Baseline end = EDATE(StartMonth,[Starts in month]+[Value]-2)
Baseline end = MAX(J29:[Baseline end, row above])
Forecast start = EDATE(StartMonth,[Forecast]-1)
Forecast end = EDATE(StartMonth,[Forecast]+[Shown in titles]-2)
Forecast end = MAX(L29:[Forecast end, row above])

## Purchases
Purchases
One-off purchases and change requests. Timed by phase, so they move when the schedule moves. Paid items are in the actuals; the forecast counts the rest.
1 Purchases
Item | Supplier | Cost line | Phase | Month of phase | Baseline | Forecast | Status | Baseline month | Forecast month | Fits phase
Discovery interviews and usability tests, round 1 | Fieldnote Research | User research & testing | Design | 1 | 24000 | 24000 | Paid | 2026-05-01 | 2026-05-01 | Yes | Invoice paid in May
Device lab: 24 phones and tablets | Gadget Depot | Test devices | Build | 1 | 16000 | 17240 | Paid | 2026-07-01 | 2026-07-01 | Yes | Two extra older Android phones
Card-payment compliance review | Payment provider | Payment certification | Build | 3 | 9500 | 11200 | Paid | 2026-09-01 | 2026-09-01 | Yes | Scope grew with wallet payments (CR-01)
Usability tests with beta users, round 2 | Fieldnote Research | User research & testing | Launch prep | 1 | 18000 | 18000 | Committed | 2026-12-01 | 2026-12-01 | Yes | Purchase order raised
Penetration test | Redwall Security | Security & accessibility | Launch prep | 1 | 32000 | 34500 | Committed | 2026-12-01 | 2026-12-01 | Yes | Quote received 2 Oct, higher than the estimate
Accessibility audit (WCAG 2.2 AA) | Clearpath Access | Security & accessibility | Launch prep | 2 | 14000 | 14000 | Planned | 2027-01-01 | 2027-01-01 | Yes
Older and foldable test phones | Gadget Depot | Test devices | Launch prep | 1 | 0 | 3800 | Planned | 2026-12-01 | 2026-12-01 | Yes | New: crashes on older phones in the first beta
Store screenshots, preview video and launch film | Studio Marlow | Launch content | Launch prep | 2 | 22000 | 22000 | Planned | 2027-01-01 | 2027-01-01 | Yes
Total |  |  |  |  | 135500 | 144740
2 Change requests
Fixed bids from the development agencies for scope added after the baseline. Approved ones are funded from the contingency.
Change | Reference | Status | Month |  | Cost | In forecast
Apple Pay and Google Pay at checkout | CR-01 | Approved | 2026-11-01 |  | 38000 | Yes |  |  |  |  | Approved 21 Aug
Allergen and nutrition info from the menu system | CR-02 | Approved | 2026-12-01 |  | 21500 | Yes |  |  |  |  | Approved 18 Sep
Gift cards in the app | CR-03 | Pending | 2027-02-01 |  | 46000 | No |  |  |  |  | Decision at the October steering committee
Apple Watch app | CR-04 | Rejected | 2027-03-01 |  | 64000 | No |  |  |  |  | Rejected 18 Sep: after launch, if at all
Approved |  |  |  |  | 59500
Pending |  |  |  |  | 46000
Formulas:
Baseline month = IF([Phase]="","",EDATE(StartMonth,INDEX(BaseStarts,MATCH([Phase],PhaseNames,0))+[Month of phase]-2))
Forecast month = IF([Phase]="","",EDATE(StartMonth,INDEX(FcStarts,MATCH([Phase],PhaseNames,0))+[Month of phase]-2))

## Actuals
Actuals
The project's costs as booked by finance: one row per invoice, payroll allocation, accrual or credit note. Paste each month's export at the bottom of the table.
Rows | 64 | Total | 826535 | Closed through | 2026-09-01
Latest | 2026-09-01 | Ignored | 0 rows after the last closed month (shown grey)
Period | Cost line | Supplier | Description | Reference | Amount
2026-04-01 | Product management | Payroll allocation | Apr 2026: 1 FTE at standard cost | JNL-2604-01 | 14500
2026-04-01 | Product design | Payroll allocation | Apr 2026: 1 FTE at standard cost | JNL-2604-02 | 12500
2026-04-01 | Backend & integrations | Payroll allocation | Apr 2026: 0.5 FTE at standard cost | JNL-2604-03 | 7000
2026-04-01 | Cloud & DevOps | Payroll allocation | Apr 2026: 0.25 FTE at standard cost | JNL-2604-04 | 3625
2026-04-01 | Engineering lead | Payroll allocation | Apr 2026: 0.5 FTE at standard cost | JNL-2604-05 | 8250
2026-04-01 | Cloud hosting | Cloud provider | Apr 2026: Monthly usage invoice | INV-2604-06 | 380
2026-04-01 | Software & tools | Tool subscriptions | Apr 2026: Design, code, test and monitoring tools | INV-2604-07 | 1800
2026-05-01 | Product management | Payroll allocation | May 2026: 1 FTE at standard cost | JNL-2605-01 | 14500
2026-05-01 | Product design | Payroll allocation | May 2026: 1.5 FTE at standard cost | JNL-2605-02 | 18750
2026-05-01 | iOS development | Brightlane Studio | May 2026: 8 days at $780 | INV-2605-03 | 6240
2026-05-01 | Android development | Parallel Apps | May 2026: 9 days at $760 | INV-2605-04 | 6840
2026-05-01 | Backend & integrations | Payroll allocation | May 2026: 1 FTE at standard cost | JNL-2605-05 | 14000
2026-05-01 | Cloud & DevOps | Payroll allocation | May 2026: 0.25 FTE at standard cost | JNL-2605-06 | 3625
2026-05-01 | Engineering lead | Payroll allocation | May 2026: 1 FTE at standard cost | JNL-2605-07 | 16500
2026-05-01 | Cloud hosting | Cloud provider | May 2026: Monthly usage invoice | INV-2605-08 | 1140
2026-05-01 | Software & tools | Tool subscriptions | May 2026: Design, code, test and monitoring tools | INV-2605-09 | 3350
2026-05-01 | Third-party services | API services | May 2026: Maps, push notifications and text messages | INV-2605-10 | 210
2026-05-01 | User research & testing | Fieldnote Research | Discovery interviews and usability tests, round 1 | INV-2605-11 | 24000
2026-06-01 | Product management | Payroll allocation | Jun 2026: 1 FTE at standard cost | JNL-2606-01 | 14500
2026-06-01 | Product design | Payroll allocation | Jun 2026: 2 FTE at standard cost | JNL-2606-02 | 25000
2026-06-01 | iOS development | Brightlane Studio | Jun 2026: 9 days at $780 | INV-2606-03 | 7020
2026-06-01 | Android development | Parallel Apps | Jun 2026: 9 days at $760 | INV-2606-04 | 6840
2026-06-01 | Backend & integrations | Payroll allocation | Jun 2026: 1 FTE at standard cost | JNL-2606-05 | 14000
2026-06-01 | Cloud & DevOps | Payroll allocation | Jun 2026: 0.25 FTE at standard cost | JNL-2606-06 | 3625
2026-06-01 | Engineering lead | Payroll allocation | Jun 2026: 1 FTE at standard cost | JNL-2606-07 | 16500
2026-06-01 | Cloud hosting | Cloud provider | Jun 2026: Monthly usage invoice | INV-2606-08 | 1260
2026-06-01 | Software & tools | Tool subscriptions | Jun 2026: Design, code, test and monitoring tools | INV-2606-09 | 3200
2026-06-01 | Third-party services | API services | Jun 2026: Maps, push notifications and text messages | INV-2606-10 | 340
2026-07-01 | Product management | Payroll allocation | Jul 2026: 1 FTE at standard cost | JNL-2607-01 | 14500
2026-07-01 | Product design | Payroll allocation | Jul 2026: 0.75 FTE at standard cost | JNL-2607-02 | 9375
2026-07-01 | iOS development | Brightlane Studio | Jul 2026: 35 days at $780 | INV-2607-03 | 27300
2026-07-01 | Android development | Parallel Apps | Jul 2026: 36 days at $760 | INV-2607-04 | 27360
2026-07-01 | Backend & integrations | Payroll allocation | Jul 2026: 3 FTE at standard cost | JNL-2607-05 | 42000
2026-07-01 | Quality assurance | TestHarbor | Jul 2026: 27 days at $560 | INV-2607-06 | 15120
2026-07-01 | Cloud & DevOps | Payroll allocation | Jul 2026: 0.5 FTE at standard cost | JNL-2607-07 | 7250
2026-07-01 | Engineering lead | Payroll allocation | Jul 2026: 1 FTE at standard cost | JNL-2607-08 | 16500
2026-07-01 | Cloud hosting | Cloud provider | Jul 2026: Monthly usage invoice | INV-2607-09 | 6120
2026-07-01 | Software & tools | Tool subscriptions | Jul 2026: Design, code, test and monitoring tools | INV-2607-10 | 5400
2026-07-01 | Third-party services | API services | Jul 2026: Maps, push notifications and text messages | INV-2607-11 | 1450
2026-07-01 | Test devices | Gadget Depot | Device lab: 24 phones and tablets | INV-2607-12 | 17240
2026-08-01 | Product management | Payroll allocation | Aug 2026: 1 FTE at standard cost | JNL-2608-01 | 14500
2026-08-01 | Product design | Payroll allocation | Aug 2026: 0.75 FTE at standard cost | JNL-2608-02 | 9375
2026-08-01 | iOS development | Brightlane Studio | Aug 2026: 36 days at $780 | INV-2608-03 | 28080
2026-08-01 | Android development | Parallel Apps | Aug 2026: 45 days at $760 | INV-2608-04 | 34200
2026-08-01 | Backend & integrations | Payroll allocation | Aug 2026: 3 FTE at standard cost | JNL-2608-05 | 42000
2026-08-01 | Quality assurance | TestHarbor | Aug 2026: 30 days at $560 | INV-2608-06 | 16800
2026-08-01 | Cloud & DevOps | Payroll allocation | Aug 2026: 0.5 FTE at standard cost | JNL-2608-07 | 7250
2026-08-01 | Engineering lead | Payroll allocation | Aug 2026: 1 FTE at standard cost | JNL-2608-08 | 16500
2026-08-01 | Cloud hosting | Cloud provider | Aug 2026: Monthly usage invoice | INV-2608-09 | 6940
2026-08-01 | Software & tools | Tool subscriptions | Aug 2026: Design, code, test and monitoring tools | INV-2608-10 | 5400
2026-08-01 | Third-party services | API services | Aug 2026: Maps, push notifications and text messages | INV-2608-11 | 1920
2026-08-01 | Software & tools | Tool subscriptions | Credit note: two unused design seats | CRN-2608-01 | -480
2026-09-01 | Product management | Payroll allocation | Sep 2026: 1 FTE at standard cost | JNL-2609-01 | 14500
2026-09-01 | Product design | Payroll allocation | Sep 2026: 0.75 FTE at standard cost | JNL-2609-02 | 9375
2026-09-01 | iOS development | Brightlane Studio | Accrual: Sep 2026 work, 37 days at $780, invoice not yet received | ACC-2609-01 | 28860
2026-09-01 | Android development | Parallel Apps | Sep 2026: 45 days at $760 | INV-2609-04 | 34200
2026-09-01 | Backend & integrations | Payroll allocation | Sep 2026: 3 FTE at standard cost | JNL-2609-05 | 42000
2026-09-01 | Quality assurance | TestHarbor | Sep 2026: 36 days at $560 | INV-2609-06 | 20160
2026-09-01 | Cloud & DevOps | Payroll allocation | Sep 2026: 0.75 FTE at standard cost | JNL-2609-07 | 10875
2026-09-01 | Engineering lead | Payroll allocation | Sep 2026: 1 FTE at standard cost | JNL-2609-08 | 16500
2026-09-01 | Cloud hosting | Cloud provider | Sep 2026: Monthly usage invoice | INV-2609-09 | 9860
2026-09-01 | Software & tools | Tool subscriptions | Sep 2026: Design, code, test and monitoring tools | INV-2609-10 | 5100
2026-09-01 | Third-party services | API services | Sep 2026: Maps, push notifications and text messages | INV-2609-11 | 2310
2026-09-01 | Payment certification | Payment provider | Card-payment compliance review | INV-2609-12 | 11200

## Calc
Calc
How the numbers are made, month by month. Formulas only: nothing to type here.
Month number |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Month |  | Total | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01
Actual or forecast |  |  | Actual | Actual | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
Closed month (1 = actuals) | flag |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baseline phase number | phase |  | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 0 | 0 | 0
Baseline phase |  |  | Discovery | Design | Design | Build | Build | Build | Build | Build | Launch prep | Launch prep | Hypercare | Hypercare | – | – | –
Forecast phase number | phase |  | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 0 | 0 | 0
Forecast phase |  |  | Discovery | Design | Design | Build | Build | Build | Build | Build | Launch prep | Launch prep | Hypercare | Hypercare | – | – | –
1 Team, baseline: staffing
FTE per month from the baseline schedule and staffing (Inputs 3 and 6).
Product management | FTE | 11 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0
Product design | FTE | 11.5 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.25 | 0.25 | 0 | 0 | 0
iOS development | FTE | 16 | 0 | 0.5 | 0.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0.5 | 0 | 0 | 0
Android development | FTE | 16 | 0 | 0.5 | 0.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0.5 | 0 | 0 | 0
Backend & integrations | FTE | 23.5 | 0.5 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Quality assurance | FTE | 12.5 | 0 | 0 | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 2 | 2 | 0.5 | 0.5 | 0 | 0 | 0
Cloud & DevOps | FTE | 6.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0
Engineering lead | FTE | 10.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0
Team size |  | 107.25 | 3.25 | 6.25 | 6.25 | 12 | 12 | 12 | 12 | 12 | 11.5 | 11.5 | 4.25 | 4.25 | 0 | 0 | 0
2 Team, baseline: cost
FTE × baseline cost per FTE month (Inputs 5).
Product management | Internal | 159500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 7250 | 7250 | 0 | 0 | 0
Product design | Internal | 143750 | 12500 | 25000 | 25000 | 12500 | 12500 | 12500 | 12500 | 12500 | 6250 | 6250 | 3125 | 3125 | 0 | 0 | 0
iOS development | Contractor | 224640 | 0 | 7020 | 7020 | 28080 | 28080 | 28080 | 28080 | 28080 | 28080 | 28080 | 7020 | 7020 | 0 | 0 | 0
Android development | Contractor | 218880 | 0 | 6840 | 6840 | 27360 | 27360 | 27360 | 27360 | 27360 | 27360 | 27360 | 6840 | 6840 | 0 | 0 | 0
Backend & integrations | Internal | 329000 | 7000 | 14000 | 14000 | 42000 | 42000 | 42000 | 42000 | 42000 | 28000 | 28000 | 14000 | 14000 | 0 | 0 | 0
Quality assurance | Contractor | 126000 | 0 | 0 | 0 | 15120 | 15120 | 15120 | 15120 | 15120 | 20160 | 20160 | 5040 | 5040 | 0 | 0 | 0
Cloud & DevOps | Internal | 90625 | 3625 | 3625 | 3625 | 7250 | 7250 | 7250 | 7250 | 7250 | 14500 | 14500 | 7250 | 7250 | 0 | 0 | 0
Engineering lead | Internal | 173250 | 8250 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 8250 | 8250 | 0 | 0 | 0
Team, baseline |  | 1465645 | 45875 | 87485 | 87485 | 163310 | 163310 | 163310 | 163310 | 163310 | 155350 | 155350 | 58775 | 58775 | 0 | 0 | 0
3 Team, current plan: staffing
FTE per month from the forecast schedule and current staffing, before actuals replace the closed months.
Product management | FTE | 11 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0
Product design | FTE | 10.25 | 1 | 2 | 2 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.5 | 0.5 | 0.25 | 0.25 | 0 | 0 | 0
iOS development | FTE | 16 | 0 | 0.5 | 0.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0.5 | 0 | 0 | 0
Android development | FTE | 19.5 | 0 | 0.5 | 0.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0.5 | 0.5 | 0 | 0 | 0
Backend & integrations | FTE | 23.5 | 0.5 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Quality assurance | FTE | 15 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0.5 | 0 | 0 | 0
Cloud & DevOps | FTE | 6.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0
Engineering lead | FTE | 10.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0
Team size |  | 112 | 3.25 | 6.25 | 6.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12 | 12 | 4.25 | 4.25 | 0 | 0 | 0
4 Team, current plan: cost
FTE × forecast cost per FTE month (current rates and the what-if rate change).
Product management | Internal | 159500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 7250 | 7250 | 0 | 0 | 0
Product design | Internal | 128125 | 12500 | 25000 | 25000 | 9375 | 9375 | 9375 | 9375 | 9375 | 6250 | 6250 | 3125 | 3125 | 0 | 0 | 0
iOS development | Contractor | 224640 | 0 | 7020 | 7020 | 28080 | 28080 | 28080 | 28080 | 28080 | 28080 | 28080 | 7020 | 7020 | 0 | 0 | 0
Android development | Contractor | 266760 | 0 | 6840 | 6840 | 34200 | 34200 | 34200 | 34200 | 34200 | 34200 | 34200 | 6840 | 6840 | 0 | 0 | 0
Backend & integrations | Internal | 329000 | 7000 | 14000 | 14000 | 42000 | 42000 | 42000 | 42000 | 42000 | 28000 | 28000 | 14000 | 14000 | 0 | 0 | 0
Quality assurance | Contractor | 159300 | 0 | 0 | 0 | 21240 | 21240 | 21240 | 21240 | 21240 | 21240 | 21240 | 5310 | 5310 | 0 | 0 | 0
Cloud & DevOps | Internal | 90625 | 3625 | 3625 | 3625 | 7250 | 7250 | 7250 | 7250 | 7250 | 14500 | 14500 | 7250 | 7250 | 0 | 0 | 0
Engineering lead | Internal | 173250 | 8250 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 8250 | 8250 | 0 | 0 | 0
Team, current plan |  | 1531200 | 45875 | 87485 | 87485 | 173145 | 173145 | 173145 | 173145 | 173145 | 163270 | 163270 | 59045 | 59045 | 0 | 0 | 0
5 Platform & tools, baseline
Monthly run-rate of the phase each month falls in (Inputs 7).
Cloud hosting | per month | 70300 | 400 | 1200 | 1200 | 5500 | 5500 | 5500 | 5500 | 5500 | 8000 | 8000 | 12000 | 12000 | 0 | 0 | 0
Software & tools | per month | 54000 | 1800 | 3200 | 3200 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 4000 | 4000 | 0 | 0 | 0
Third-party services | per month | 21800 | 0 | 300 | 300 | 1800 | 1800 | 1800 | 1800 | 1800 | 2600 | 2600 | 3500 | 3500 | 0 | 0 | 0
Platform, baseline |  | 146100 | 2200 | 4700 | 4700 | 12700 | 12700 | 12700 | 12700 | 12700 | 16000 | 16000 | 19500 | 19500 | 0 | 0 | 0
6 Platform & tools, current plan
Cloud hosting | per month | 81800 | 400 | 1200 | 1200 | 7200 | 7200 | 7200 | 7200 | 7200 | 9000 | 9000 | 12500 | 12500 | 0 | 0 | 0
Software & tools | per month | 51900 | 1800 | 3200 | 3200 | 5100 | 5100 | 5100 | 5100 | 5100 | 5100 | 5100 | 4000 | 4000 | 0 | 0 | 0
Third-party services | per month | 21800 | 0 | 300 | 300 | 1800 | 1800 | 1800 | 1800 | 1800 | 2600 | 2600 | 3500 | 3500 | 0 | 0 | 0
Platform, current plan |  | 155500 | 2200 | 4700 | 4700 | 14100 | 14100 | 14100 | 14100 | 14100 | 16700 | 16700 | 20000 | 20000 | 0 | 0 | 0
7 Vendors & purchases, baseline
Baseline amounts in the baseline month (Purchases 1).
User research & testing |  | 42000 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0
Security & accessibility |  | 46000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 14000 | 0 | 0 | 0 | 0 | 0
Payment certification |  | 9500 | 0 | 0 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test devices |  | 16000 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Launch content |  | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0
Vendors, baseline |  | 135500 | 0 | 24000 | 0 | 16000 | 0 | 9500 | 0 | 0 | 50000 | 36000 | 0 | 0 | 0 | 0 | 0
8 Vendors & purchases, current plan
Forecast amounts in the forecast month, without items already paid.
User research & testing |  | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0
Security & accessibility |  | 48500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34500 | 14000 | 0 | 0 | 0 | 0 | 0
Payment certification |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test devices |  | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0
Launch content |  | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0
Vendors, current plan |  | 92300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56300 | 36000 | 0 | 0 | 0 | 0 | 0
9 Change requests
Fixed bids in the month they are invoiced (Purchases 2).
Approved change requests |  | 59500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 | 21500 | 0 | 0 | 0 | 0 | 0 | 0
Pending change requests (what-if) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Changes, current plan |  | 59500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 | 21500 | 0 | 0 | 0 | 0 | 0 | 0
10 Baseline plan by cost line
The approved plan. The budget on Report is each row's total.
Product management | Team | 159500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 7250 | 7250 | 0 | 0 | 0
Product design | Team | 143750 | 12500 | 25000 | 25000 | 12500 | 12500 | 12500 | 12500 | 12500 | 6250 | 6250 | 3125 | 3125 | 0 | 0 | 0
iOS development | Team | 224640 | 0 | 7020 | 7020 | 28080 | 28080 | 28080 | 28080 | 28080 | 28080 | 28080 | 7020 | 7020 | 0 | 0 | 0
Android development | Team | 218880 | 0 | 6840 | 6840 | 27360 | 27360 | 27360 | 27360 | 27360 | 27360 | 27360 | 6840 | 6840 | 0 | 0 | 0
Backend & integrations | Team | 329000 | 7000 | 14000 | 14000 | 42000 | 42000 | 42000 | 42000 | 42000 | 28000 | 28000 | 14000 | 14000 | 0 | 0 | 0
Quality assurance | Team | 126000 | 0 | 0 | 0 | 15120 | 15120 | 15120 | 15120 | 15120 | 20160 | 20160 | 5040 | 5040 | 0 | 0 | 0
Cloud & DevOps | Team | 90625 | 3625 | 3625 | 3625 | 7250 | 7250 | 7250 | 7250 | 7250 | 14500 | 14500 | 7250 | 7250 | 0 | 0 | 0
Engineering lead | Team | 173250 | 8250 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 8250 | 8250 | 0 | 0 | 0
User research & testing | Purchases | 42000 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0
Security & accessibility | Purchases | 46000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 14000 | 0 | 0 | 0 | 0 | 0
Payment certification | Purchases | 9500 | 0 | 0 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test devices | Purchases | 16000 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Launch content | Purchases | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0
Cloud hosting | Platform | 70300 | 400 | 1200 | 1200 | 5500 | 5500 | 5500 | 5500 | 5500 | 8000 | 8000 | 12000 | 12000 | 0 | 0 | 0
Software & tools | Platform | 54000 | 1800 | 3200 | 3200 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 4000 | 4000 | 0 | 0 | 0
Third-party services | Platform | 21800 | 0 | 300 | 300 | 1800 | 1800 | 1800 | 1800 | 1800 | 2600 | 2600 | 3500 | 3500 | 0 | 0 | 0
Approved changes | Changes | 0
Baseline plan |  | 1747245 | 48075 | 116185 | 92185 | 192010 | 176010 | 185510 | 176010 | 176010 | 221350 | 207350 | 78275 | 78275 | 0 | 0 | 0
11 Actuals by cost line
From the Actuals table, closed months only.
Product management | Team | 87000 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Product design | Team | 84375 | 12500 | 18750 | 25000 | 9375 | 9375 | 9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
iOS development | Team | 97500 | 0 | 6240 | 7020 | 27300 | 28080 | 28860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Android development | Team | 109440 | 0 | 6840 | 6840 | 27360 | 34200 | 34200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Backend & integrations | Team | 161000 | 7000 | 14000 | 14000 | 42000 | 42000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality assurance | Team | 52080 | 0 | 0 | 0 | 15120 | 16800 | 20160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cloud & DevOps | Team | 36250 | 3625 | 3625 | 3625 | 7250 | 7250 | 10875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering lead | Team | 90750 | 8250 | 16500 | 16500 | 16500 | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User research & testing | Purchases | 24000 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Security & accessibility | Purchases | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Payment certification | Purchases | 11200 | 0 | 0 | 0 | 0 | 0 | 11200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test devices | Purchases | 17240 | 0 | 0 | 0 | 17240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Launch content | Purchases | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cloud hosting | Platform | 25700 | 380 | 1140 | 1260 | 6120 | 6940 | 9860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software & tools | Platform | 23770 | 1800 | 3350 | 3200 | 5400 | 4920 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Third-party services | Platform | 6230 | 0 | 210 | 340 | 1450 | 1920 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Approved changes | Changes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actuals |  | 826535 | 48055 | 109155 | 92285 | 189615 | 182485 | 204940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 Forecast by cost line
The current plan, for the months after the last closed month.
Product management | Team | 72500 | 0 | 0 | 0 | 0 | 0 | 0 | 14500 | 14500 | 14500 | 14500 | 7250 | 7250 | 0 | 0 | 0
Product design | Team | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 9375 | 9375 | 6250 | 6250 | 3125 | 3125 | 0 | 0 | 0
iOS development | Team | 126360 | 0 | 0 | 0 | 0 | 0 | 0 | 28080 | 28080 | 28080 | 28080 | 7020 | 7020 | 0 | 0 | 0
Android development | Team | 150480 | 0 | 0 | 0 | 0 | 0 | 0 | 34200 | 34200 | 34200 | 34200 | 6840 | 6840 | 0 | 0 | 0
Backend & integrations | Team | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 42000 | 28000 | 28000 | 14000 | 14000 | 0 | 0 | 0
Quality assurance | Team | 95580 | 0 | 0 | 0 | 0 | 0 | 0 | 21240 | 21240 | 21240 | 21240 | 5310 | 5310 | 0 | 0 | 0
Cloud & DevOps | Team | 58000 | 0 | 0 | 0 | 0 | 0 | 0 | 7250 | 7250 | 14500 | 14500 | 7250 | 7250 | 0 | 0 | 0
Engineering lead | Team | 82500 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | 16500 | 16500 | 16500 | 8250 | 8250 | 0 | 0 | 0
User research & testing | Purchases | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0
Security & accessibility | Purchases | 48500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34500 | 14000 | 0 | 0 | 0 | 0 | 0
Payment certification | Purchases | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test devices | Purchases | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0
Launch content | Purchases | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0
Cloud hosting | Platform | 57400 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 7200 | 9000 | 9000 | 12500 | 12500 | 0 | 0 | 0
Software & tools | Platform | 28400 | 0 | 0 | 0 | 0 | 0 | 0 | 5100 | 5100 | 5100 | 5100 | 4000 | 4000 | 0 | 0 | 0
Third-party services | Platform | 15800 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 2600 | 2600 | 3500 | 3500 | 0 | 0 | 0
Approved changes | Changes | 59500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 | 21500 | 0 | 0 | 0 | 0 | 0 | 0
Forecast |  | 1044320 | 0 | 0 | 0 | 0 | 0 | 0 | 187245 | 225245 | 257770 | 215970 | 79045 | 79045 | 0 | 0 | 0
13 Actual + forecast by cost line
What each line will have cost by the end: actuals so far, forecast after.
Product management | Team | 159500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500 | 7250 | 7250 | 0 | 0 | 0
Product design | Team | 121875 | 12500 | 18750 | 25000 | 9375 | 9375 | 9375 | 9375 | 9375 | 6250 | 6250 | 3125 | 3125 | 0 | 0 | 0
iOS development | Team | 223860 | 0 | 6240 | 7020 | 27300 | 28080 | 28860 | 28080 | 28080 | 28080 | 28080 | 7020 | 7020 | 0 | 0 | 0
Android development | Team | 259920 | 0 | 6840 | 6840 | 27360 | 34200 | 34200 | 34200 | 34200 | 34200 | 34200 | 6840 | 6840 | 0 | 0 | 0
Backend & integrations | Team | 329000 | 7000 | 14000 | 14000 | 42000 | 42000 | 42000 | 42000 | 42000 | 28000 | 28000 | 14000 | 14000 | 0 | 0 | 0
Quality assurance | Team | 147660 | 0 | 0 | 0 | 15120 | 16800 | 20160 | 21240 | 21240 | 21240 | 21240 | 5310 | 5310 | 0 | 0 | 0
Cloud & DevOps | Team | 94250 | 3625 | 3625 | 3625 | 7250 | 7250 | 10875 | 7250 | 7250 | 14500 | 14500 | 7250 | 7250 | 0 | 0 | 0
Engineering lead | Team | 173250 | 8250 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 8250 | 8250 | 0 | 0 | 0
User research & testing | Purchases | 42000 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0
Security & accessibility | Purchases | 48500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34500 | 14000 | 0 | 0 | 0 | 0 | 0
Payment certification | Purchases | 11200 | 0 | 0 | 0 | 0 | 0 | 11200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test devices | Purchases | 21040 | 0 | 0 | 0 | 17240 | 0 | 0 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0
Launch content | Purchases | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0
Cloud hosting | Platform | 83100 | 380 | 1140 | 1260 | 6120 | 6940 | 9860 | 7200 | 7200 | 9000 | 9000 | 12500 | 12500 | 0 | 0 | 0
Software & tools | Platform | 52170 | 1800 | 3350 | 3200 | 5400 | 4920 | 5100 | 5100 | 5100 | 5100 | 5100 | 4000 | 4000 | 0 | 0 | 0
Third-party services | Platform | 22030 | 0 | 210 | 340 | 1450 | 1920 | 2310 | 1800 | 1800 | 2600 | 2600 | 3500 | 3500 | 0 | 0 | 0
Approved changes | Changes | 59500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 | 21500 | 0 | 0 | 0 | 0 | 0 | 0
Actual + forecast |  | 1870855 | 48055 | 109155 | 92285 | 189615 | 182485 | 204940 | 187245 | 225245 | 257770 | 215970 | 79045 | 79045 | 0 | 0 | 0
14 Cumulative
Baseline plan, cumulative |  |  | 48075 | 164260 | 256445 | 448455 | 624465 | 809975 | 985985 | 1161995 | 1383345 | 1590695 | 1668970 | 1747245 | 1747245 | 1747245 | 1747245
Actual + forecast, cumulative |  |  | 48055 | 157210 | 249495 | 439110 | 621595 | 826535 | 1013780 | 1239025 | 1496795 | 1712765 | 1791810 | 1870855 | 1870855 | 1870855 | 1870855
15 Every booking by cost line
All rows on Actuals, any month. Check 1 compares the total with the table's.
Product management | Team | 87000
Product design | Team | 84375
iOS development | Team | 97500
Android development | Team | 109440
Backend & integrations | Team | 161000
Quality assurance | Team | 52080
Cloud & DevOps | Team | 36250
Engineering lead | Team | 90750
User research & testing | Purchases | 24000
Security & accessibility | Purchases | 0
Payment certification | Purchases | 11200
Test devices | Purchases | 17240
Launch content | Purchases | 0
Cloud hosting | Platform | 25700
Software & tools | Platform | 23770
Third-party services | Platform | 6230
Approved changes | Changes | 0
Every booking |  | 826535

## Checks
Checks
Tests the model runs on itself. Each result is OK or FAIL; the count shows on the Cover and the Dashboard.
Result | All 14 checks pass | 0
# | Check | Value | Result | If it fails
1 | Every actual has a cost line from the list | 0 | OK | A row on Actuals uses a cost line that isn't on Inputs. Pick one from the list.
2 | No actuals dated before the project started | 0 | OK | Move the row to a project month or delete it.
3 | No actuals after the last closed month | 0 | OK | Rows after Actuals through are ignored. Move Actuals through, or wait for finance to close that month.
4 | Every closed month has actuals | 0 | OK | A closed month has no actuals: paste its export on Actuals, or move Actuals through back.
5 | Actuals through falls inside the timeline | 0 | OK | Pick a month from the list on Inputs.
6 | The baseline is still the approved plan | 0 | OK | A baseline input changed. Put the change in a current column instead, or record a re-baseline.
7 | The forecast schedule fits the timeline | 0 | OK | The phases run past month 15. The model covers 15 months: shorten the phases or add months.
8 | Every purchase fits inside its phase | 0 | OK | A purchase's month of phase is beyond the phase's length. Change the month or the phase.
9 | Unpaid purchases are not in closed months | 0 | OK | An unpaid item falls in a closed month, so the forecast drops it. Mark it Paid or move it.
10 | Changes in the forecast are inside the timeline | 0 | OK | A change request in the forecast has a month outside the timeline.
11 | No negative staffing or amounts in the plan | 0 | OK | Staffing, run-rates and purchase amounts can't be negative.
12 | Report total = sum of all monthly lines | 0 | OK | The Report and Calc disagree: a formula was overwritten.
13 | Monthly view total = Report total | 0 | OK | The Monthly view and the Report disagree: a formula was overwritten.
14 | Phase budgets add up to the base budget | 0 | OK | Some baseline cost falls outside every phase.